## Benefits Realization Plan
Business Benefits Realization Plan
Project Name | Mobile check-in
Project Manager | Laura Paton
Benefit ID | B-001 | B-002 | [ID] | [ID] | [ID]
Benefit name | Front desk staff reduction
Benefit owner | Tammy Marley-Cox Director of Hospitality, North America
Benefit type | Cost reduction
Expected Value | $500,000 annual savings
Benefit start | 08/01/2021 12/31/2021
Benefit end | 2021-12-31
Metrics/KPIs | % of guests checking in via mobile app versus in lobby
Measurement process | Guest counts can be determined by running a query from both the mobile app and front desk reservation systems. IT will prepare a query and make it available for Hotel Ops to run on-demand
Data collection owner | Director of Hotel Operations
Frequency | Monthly first six months after application roll-out and quarterly thereafter
Key stakeholders | Director of Hotel Operations HR manager VP Resorts Guest Relations Manager
Assumptions | Mobile app will be rolled out by year-end
Risks | The mobile app is being developed by a third party vendor we have not done work with before. While contractually the SOW is solid, careful monitoring of vendor performance is required to ensure the project stays on track.